EEN1095 Project Progress and Change Log

| Student Name | Darshan Mahadeva Naika | Student ID | A0090581 |
| --- | --- | --- | --- |
| Project Title | Design and Evaluation of Low-Sensitivity Digital Filters Implemented in Python Under Varying Numerical Precision Levels | Supervisor | Martin Collier |
| Implementation Period | Week 1 - Week X | Version Date | 22/05/2026 |

Guidance: Maintain this as one cumulative document throughout EEN1095. Add a new entry every two weeks and do not remove earlier records. Progress should be recorded in a timely and concise manner. Where no change has occurred, this should be stated explicitly.

- Project Overview

| Original approved project title | Design and Evaluation of Low-Sensitivity Digital Filters Implemented in Python Under Varying Numerical Precision Levels |
| --- | --- |
| Original project objectives | Evaluate three IIR filter structures (Direct-Form, Ladder, WDF) and FIR filters across four Python precision levels (float16, float32, float64, mpmath) using five quantitative metrics to determine whether structure or precision is the primary robustness driver. |
| Original proposed methodology | Systematic multi-precision comparative evaluation in Python 3.11 using NumPy, SciPy, and mpmath. All filters designed via SciPy with transition bandwidth 0.02. Metrics computed: pole displacement, stability margin, sensitivity norm, frequency response deviation, roundoff noise. |
| Planned outputs / deliverables | Complete Python multi-precision evaluation framework; experimental results dataset; comparative analysis tables and figures; final project report (August 2026); open-source Python tool for precision-aware filter design. |

- Summary of Key Milestones

The table below is intended as a high-level summary. Use Section 3 for the detailed bi-weekly updates.

| Period | Planned activity | Progress made | Outcome / status |
| --- | --- | --- | --- |
| Weeks 1-2 | Begin Python multi-precision framework development. Set up NumPy, SciPy, and mpmath. Validate precision control for float16, float32, float64, and mpmath. | Python framework structure established. Precision control for float16, float32, float64, and mpmath confirmed working. Pilot filter design tested using SciPy. | In Progress — M3: Python framework validated at all 4 precision levels |
| Weeks 3-4 | Complete Python framework validation. Implement direct-form IIR evaluation module. Run pilot experiments for order-10 and order-20 IIR designs. | Not yet reached. Scheduled for next period. | Upcoming |
| Weeks 5-6 | Implement ladder filter Python module. Validate against direct-form baseline. | Not yet reached. Scheduled for June 2026. | Upcoming — M4: All filter structures implemented and validated |
| Weeks 7-8 | Implement WDF Python module. Begin full IIR experimental evaluation across all 144 configurations. | Not yet reached. Scheduled for June 2026. | Upcoming — M5: Complete experimental dataset collected |
| Weeks 9-10 | Complete full IIR and FIR experimental evaluation. Collect complete results dataset. | Not yet reached. Scheduled for June–July 2026. | Upcoming |
| Weeks 11-12 | Perform cross-precision statistical analysis. Produce comparative tables and figures. | Not yet reached. Scheduled for July 2026. | Upcoming — M6: Analysis and comparative figures complete |
| Weeks 13-14 | Write and submit final project report. Publish open-source Python framework. | Not yet reached. Scheduled for August 2026. | Upcoming — M7: Final report submitted |

- Detailed Progress Entries

Entry 1: Weeks 1-2

| Main objectives for this period | Begin Python multi-precision framework development using NumPy, SciPy, and mpmath. Set up and validate precision control for float16, float32, float64, and mpmath. Run pilot filter design tests using SciPy. |
| --- | --- |
| Work completed | Python framework structure established. NumPy dtype selection confirmed working for float16, float32, and float64. mpmath precision control via mp.dps = 50 confirmed working. Pilot filter design tested using SciPy scipy.signal for Butterworth and elliptic IIR designs. SciPy SOS format validated for numerical accuracy in high-order IIR designs. |
| Key outputs produced | Python framework files: filter_design.py, core filter design and precision conversion module. metrics.py, five performance metrics module. experiment.py, experimental evaluation runner. Pilot results for order-10 and order-20 direct-form IIR designs across all four precision levels. |
| Problems encountered | No significant problems encountered. Minor issue with mpmath coefficient conversion from SciPy float64 arrays, resolved by converting each coefficient individually using mpmath.mpf(str(c)) to avoid floating-point representation errors during conversion. |
| Changes made to plan or methodology | No changes to plan or methodology at this stage. Framework implementation proceeding as planned. |
| Reasons for any changes | No changes required. Python framework structure and precision control confirmed working as originally planned. |
| Next steps | Weeks 3-4 — complete full Python framework validation across all four precision levels. Implement direct-form IIR evaluation module. Run pilot experiments for order-10 and order-20 IIR designs across all precision levels and record results. |

Entry 2: Weeks 3-4

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |

Entry 3: Weeks 5-6

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |

Entry 4: Weeks 7-8

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |

Entry 5: Weeks 9-10

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |

Entry 6: Weeks 11-12

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |

Entry 7: Weeks 13-14

| Main objectives for this period | [Insert concise notes here] |
| --- | --- |
| Work completed | [Insert concise notes here] |
| Key outputs produced | [Insert concise notes here] |
| Problems encountered | [Insert concise notes here] |
| Changes made to plan or methodology | [Insert concise notes here] |
| Reasons for any changes | [Insert concise notes here] |
| Next steps | [Insert concise notes here] |